## Sheet1
CHECKLIST FOR PRIOR INSPECTION OF IN-SITU STRUCTURAL WORKS
Project Title: | [7 empty] | Date: | C1-CS-02.1_1
Block No.: |  | C1-CS-02.1_2 | Location: | C1-CS-02.1_3
(Marked Plan to be attached & initiated) |  |  |  | Gridline: |  | C1-CS-02.1_4
CHECK |  |  |  |  | YES/NO/NA
Housekeeping & Safety | 1. Clear & safe access provided along inspection area |  |  |  | C1-CS-02.1_5 |  | Checked by Builder's RSO/ Safety Supervisor
NA
| 2. Proper temporary staircase erected |  |  |  | C1-CS-02.1_6
| 3. Proper strutting work at lower storey |  |  |  | C1-CS-02.1_7
| 4. Perimeter safety barricade erected at inspection & lower floor |  |  |  | C1-CS-02.1_8
| 5. Protection to precast staircase |  |  |  | C1-CS-02.1_9
Name & Date & Time：
M&E Works | 1. Position/ Size/ Nos. of electrical conduits |  |  |  | C1-CS-02.1_10 |  | Checked by Builder's M&E Coordinator
NA
| 2. Position/ Size/ Nos. of sanitary openings |  |  |  | C1-CS-02.1_11
| 3. Trimmer bars |  |  |  | C1-CS-02.1_12
| 4. Foreign object on surface |  |  |  | C1-CS-02.1_13
Name & Date & Time：
Structural Works | 1. Typical floor defects checking and recording completed up to min. 2 levels below current casting level |  |  |  | C1-CS-02.1_14 |  | Checked by Builder's Project Engineer/ Structural Supervisor
NA
| 2. Typical floors defects rectified and closed up to min. 4 levels below current casting level |  |  |  | C1-CS-02.1_15
| 3. Submitted overall building verticality check up to min. 2 levels below current casting level |  |  |  | C1-CS-02.1_16
| 4. Submitted casted floor level record up to min. 2 levels below current casting level |  |  |  | C1-CS-02.1_17
Name & Date & Time：
| 5. Submitted soffit level check for precast plank for current casting level |  |  |  | C1-CS-02.1_18
| 6. Check to ensure no gap at joint between the formwork and precast plank, sponge to be inserted for sealing up if there is any gap along or around the joint |  |  |  | C1-CS-02.1_19
Note: Builder to complete all checks stated above before calling for inspection